## Sheet1
Task Name | Start | End | Duration
Revise Scope
Revise Needs and Wants
Restate Plan
Meeting | 2002-01-13
Implement New Needs and Wants into Design
First ProE Drawing revision
Submit ProE files to Paul
Purchase Brass | 2002-01-15
Meeting | 2002-01-16
Parts List to Kenya | 2002-01-17
Purchase Steel | 2002-01-17
Purchase Aluminum | 2002-01-17
Fabricate Rollers | 2002-01-16
Fabricate Box (BK) | 2002-01-20
Fabricate Shafts (BK) | 2002-01-20
Obtain Ordered Parts | 2002-03-10
Assemble Parts
Test Prototype
Final Design Report
Final Design Presentation