## Sheet1
6. Deliverables / 7. Assign Resources
| Task List |  | Responsibility | Due Date | Estimated Time to Finish | Expected Completion Date |  | COLOR KEY
| Website | [6 empty] | HIGH PRIORITY
|  | Group profiles | Kristian | 2013-10-18 | 2 Days | 2013-10-16 |  | MEDIUM PRIORITY
|  | Introduction to project | Kristian | 2013-10-18 | 2 Days | 2013-10-16 |  | LOW PRIORITY
|  | Team photo | Kristian | 2013-10-18 | 2 Days | 2013-10-16
|  | Upload files | Kristian | 2013-10-18 | On going | 2013-10-16
|  | Deliverables | Kristian | 2013-10-18 | 2 Days | 2013-10-16
|  | Meetings/Hours | Kristian | 2013-10-18 | On going | 2013-10-16
|  | Upload Website | Kristian | 2013-10-18 | 1 Day | 2013-10-16
Battery System
|  | General Data for Project | ALL | On Going | On Going | 2014-05-01
|  | Lifetime and size simulation | Corey | 2013-10-14 | 3 Weeks | 2013-10-14 | ** THE IMPORTANCE OF EACH GOAL WILL CHANGE AS THE DUE DATE APPROACHES**
|  | Cost analysis/ econmic benefits (Lead Acid/ LiFeP04/Li) | Anthony | 2013-10-14 | 3 Weeks | 2013-10-14
|  | Ppv simulation and modeling | Anthony | 2013-11-04 | 3 Weeks | 2013-11-04
|  | Gather previous weather data | Corey | 2013-10-18 | 1 Week | 2013-10-18
|  | Gather Ppv and Pload profiles | Corey | 2013-10-18 | 1 Week | 2013-10-18
|  | Battery Modeling | Kristian | 2013-11-18 | 3 Weeks | 2013-11-11
|  | Combination of Ppv and Battery simulation | Corey | 2013-11-04 | 2 Weeks | 2013-11-30
|  | Intergration of all simulation and results | ALL | 2013-11-25 |  | 2013-11-18
|  | Enery Management System Redisgn | ALL | 2013-10-30 |  | 2013-10-30
8/8A/9B
Has to be done with the group