## Slide 1: Spring 2018 Project Plan
2018
Today
January
February
March
April
May
Design Review 5
(03/26)
8/15/2017
Engineering Design Day
(04/09)
11/10/2017
Design Review 4
(02/26)
Graduation
(05/05)
1/8-1/19
12 days
Complete Design
1/16 - 1/26
11 days
Drawings
1/26-2/16
22 days
1/26-2/17
26 days
2/17-2/23
7 days
Build Prototype
2/26-3/5
8 days
3/2-3/30
29 days
4/26-4/30
Final Report
4/2-4/6
Final Exams
05/01-05/04
5 days
Order Parts
Manufacture Parts
Prototype Complete
(02/23)
Develop Test Rig
Test Prototype
Analyze Results
5 days
5 days
Design Review 7
(04/30)
Reevaluation
25 days
4/6-4-30

## Slide 2: Progress/Future Work (March-April)
Parts are ordered and assembly/manufacture is in progress
  Great care will be taken to ensure a speedy and successful testing process
Testing to be well underway by the end of March
  Ensure that our testing rig is sufficient, research should be done to minimize time wasted troubleshooting testing
Data to be complete by Senior Design Day (April 12)
  Compile data as we test to speed up the process.
Clean up data and reevaluate for presentation by the last week of April