## Sheet1
Milestone Number | Milestone | Task Subsets | Assigned To
1 | Customer Needs | Develop Questions for Customer | Jonathan
|  | Customer Statements (Responses) | Austin
|  | Interpreted Need From Responses | Frederick
|  | Organize into Template | Jonathan
|  | Compare to Rubric | Austin
|  | Check Work/Turn In | Patrick
2 | Project Scope | Develop a Project Description | Frederick
|  | Define Key Goals for the Project | Jonathan
|  | Define Markets | Austin
|  | Define Assumptions to Finish on Time | Patrick
|  | Define Stake Holders | Frederick
|  | Organize into Template | Jonathan
|  | Check Work with TA's | Patrick
|  | Compare to Rubric | Austin
|  | Check Work/Turn In | Patrick
3 | Functional Decomposition | Create Lowest Level Functions | Frederick
|  | Create FD Cross Reference Table | Jonathan
|  | Create FD Hierarchy Chart OR FD Flow Chart | Austin
|  | Connect the Subsystems to the Functions | Patrick
|  | Describe Physical Outcome | Frederick
|  | Define Smallest Element of the Design | Jonathan
|  | Organize into Template | Patrick
|  | Check Work with TA's | Austin
|  | Compare to Rubric | Patrick
|  | Check Work/Turn In | Patrick
4 | Targets and metrics | Create Measurable Targets from Functions | Frederick
|  | Adress Needs not Listed in Functions | Jonathan
|  | Develop Tests for Targets | Austin
|  | Define Critical Targets | Patrick
|  | Discuss How Targets were Reached | Frederick
|  | Critical Targets\Metrics | Jonathan
|  | Create Target Summary with Table | Austin
|  | Organize into Template | Patrick
|  | Check Work with TA's | Patrick
|  | Check Work/Turn In | Patrick
5 | Concept Generation | Develop Concepts | Jonathan
|  | Checkback to Targets and Metrics | Frederick
|  | Check Work/Turn In | Patrick
6 | Concept Selection | Create a House of Quality | Austin
|  | Make a Pugh Chart | Frederick
|  | Perform Analytical Hierarchy Process | Patrick
|  | Compare to Rubric | Jonathan
|  | Organize into Template | Patrick
|  | Double Check with Sponsor | Austin
|  | Check Work/Turn In | Patrick
7 | Obtain Power Train License | Ask What "online" Meant | Patrick
|  | Answer Questions | Patrick
|  | Share License Key | Patrick
8 | Understaind Power Train | Wastegate | Frederick
|  | Throttle | Jonathan
|  | Relationship of Position to Air Intake | Austin
9 | Spring Project Plan | Plan Spring Project | Patrick
|  | Create Outline | Jonathan
|  | Check Work/Turn In | Patrick
10 | Obtain GTpower | Contact Roberto Re: license | Patrick