## IDA-R
Item No. | Date Entered | Information | Decision | Action | Progress | Result | Status | Date Complete
1 | 2020-09-10 | Work on Code of Conduct | Team 516 works collectively | Code Of Conduct Assigned. | 100% | Assignment Submitted. | Complete | 2020-09-10
2 | 2020-09-10 | Sponsor Meet and Greet | Team 516 works collectively | Reach Out To Sponsor. | 100% | Email sent to sponsor. | Complete | 2020-09-09
3 | 2020-09-10 | Sponsor Meet and Greet | Team 516 works collectively | Communicate with Sponsor. | 100% | Assignment Submitted. | Complete | 2020-09-18
4 | 2020-09-10 | Project Scope | Team 516 works collectively | Description of project, what the project needs to do. | 100% | Assignment Submitted. | Complete | 2020-09-25
5 | 2020-09-10 | Customer Needs | Team 516 works collectively | Put in layman terms what needs to be done. | 100% | Assignment Submitted. | Complete | 2020-09-25
6 | 2020-09-10 | Functional Decomposition | Team 516 works collectively | Needs need to be turned into actions. | 100% | Assignment Submitted. | Complete | 2020-10-02
7 | 2020-12-15 | VDR1 Submission | Team 516 works collectively | Compile useful information to inform stakeholders of our progress. | 100% | Assignment Submitted. | Complete | 2020-10-15
8 | 2020-12-15 | First meeting with sponsor | Team 516 works collectively | Need to determine direction of project and how to go about completing the design. | 100% | First meeting with sponsor, met to discuss different concepts we would have to deal with when desigining the project, as well as challenges we would face. | Complete | 2020-10-28
9 | 2020-09-10 | Target & Metrics | Team 516 works collectively | Sponsor gives numerical values of what needs to be achieved . | 100% | Assignment Submitted. | Complete | 2020-10-30
10 | 2020-09-10 | Concept Generation & Selection | Team 516 works collectively | Brainstorm possible design solutions use selective processes to narrow down possible designs. | 100% | Assignment Submitted. | Complete | 2020-11-06
11 | 2020-12-15 | VDR2 Submission | Team 516 works collectively | Compile useful information to inform stakeholders of our progress. | 100% | Assignment Submitted. | Complete | 2020-11-13
12 | 2020-09-10 | Risk Assesment | Team 516 works collectively | Working conditions of the project. | 100% | Assignment Submitted. | Complete | 2020-12-04
13 | 2020-09-10 | Bill of Materials | Team 516 works collectively | Compile current list of all parts used in model. | 100% | Assignment Submitted. | Complete | 2020-11-24
14 | 2020-12-15 | VDR3 | Team 516 works collectively | Compile useful information to inform stakeholders of our progress. | 100% | Assignment Submitted. | Complete | 2020-12-04
15 | 2020-12-14 | Sponsor Meeting | Team 516 works collectively | Communicate with Sponsor. | 100% | Meeting completed with indepth discussion about project. | Complete | 2020-12-16
16 | 2020-09-10 | Cost Analysis | Team 516 works collectively | Assess cost associated with bill of materials. | 100% | Bill of Materials adjusted for new design. | Complete | 2021-04-01
17 | 2020-09-10 | Initial Prototype Design | Team 516 works collectively | Design working model of leveling system. | 100% | Prototype design almost completed with a few small details yet to be determined. | Complete | 2021-01-15
20 | 2021-01-11 | Finalized Calculations | Team 516 works collectively | Obtain clear and concise calculations of the system. | 100% | Calculations complete. | Complete | 2021-02-10
21 | 2021-01-11 | Finalized CAD Model | Team 516 works collectively | Obtain a properly scaled, final model. | 100% | CAD model compelte. | Complete | 2021-02-19
22 | 2021-01-11 | Prototype Construction | Team 516 works collectively | Build prototype. | 100% | Prototype construction complete. | Complete | 2021-04-01
23 | 2021-01-11 | Prototype Testing | Team 516 works collectively | Test prototype and make changes. | 100% | Prototype testing complete. | Complete | 2021-04-05
24 | 2021-01-11 | Restated Project Charter | Team 516 works collectively | Determine if aspects needed to be updated in the Code of Conduct and Project Definition. | 100% | Assignment Submitted. | Complete | 2021-01-11
25 | 2021-01-11 | Staff Meeting 1 (Spring) | Team 516 works collectively | Meeting with McConomy to disucss project progress. | 100% | Meeting completed with minutes and updated tacking document submitted. | Complete | 2021-01-15
26 | 2021-01-11 | Abstract | Team 516 works collectively | Complete abstract for project. | 100% | Abstract peer reviewed and completed. | Complete | 2021-02-05
27 | 2021-01-11 | Design Review 4 (DR4) | Team 516 works collectively | Compile useful information to inform stakeholders of our progress. | 100% | Presentation complete. | Complete | 2021-01-26
28 | 2021-01-11 | Staff Meeting 2 (Spring) | Team 516 works collectively | Meeting with McConomy to disucss project progress. | 100% | Meeting completed with minutes and updated tacking document submitted. | Complete | 2021-02-12
29 | 2021-01-11 | Design Review 5 (DR5) | Team 516 works collectively | Compile useful information to inform stakeholders of our progress. | 100% |  | Complete | 2021-02-17
30 | 2021-01-11 | Poster | Team 516 works collectively | Organize all relevant projectect information into a poster for design day. | 100% |  | Complete | 2021-03-04
31 | 2021-01-11 | Staff Meeting 3 (Spring) | Team 516 works collectively | Meeting with McConomy to disucss project progress. | 100% |  | Complete | 2021-03-10
32 | 2021-01-11 | Design Review 6 (DR6) | Team 516 works collectively | Compile useful information to inform stakeholders of our progress. | 100% |  | Complete | 2021-03-25

## Contact Log
Last Name | First Name | Full Name | email | Company | Contacted By | Date Initially Contacted | Method of First Contact | Last Contacted by | Date of Last Contact | Method of Last Contact | Information | Action | Result
McCauley | Rachel | Rachel McCauley | rachel.j.mccauley@nasa.gov | NASA | Jake Seaman | 2020-09-09 | Email | Jake Seaman | 2020-09-09 | Email

## Data Validation
Complete
Incomplete