## OPPM
Copyright OC Tanner 2007
[8 empty] | Project Instructor: Shayne McConomy |  |  |  | Project: Team 517 | [20 empty] | Date: | 2021-03-26
Project Objective: Offload the LSMS (Lightweight Surface Manipulation System) from the CLPS lander onto a platform on the lunar surface.
| Objectives | [7 empty] | Major Tasks |  |  | Project Completed By: March 30, 2020 | [19 empty] | Owner / Priority
[5 empty] | ✓ |  |  | 1 | Spring Semester Initial Meeting |  |  | ™ | ™ | [22 empty] | ✓
|  |  |  | ✓ |  |  |  | 2 | Spring Work Breakdown Structure |  |  |  | ™ | [22 empty] | ✓
| ✓ | [6 empty] | 3 | Apply For Graduation (Opens) |  |  |  |  | ™ | [21 empty] | ✓
[5 empty] | ✓ |  |  | 4 | Finalize General Design | [5 empty] | ™ | [20 empty] | ✓
[5 empty] | ✓ |  |  | 5 | CAD of General Design | [5 empty] | ™
|  |  |  | ✓ |  |  |  | 6 | Update Bill of Materials | [5 empty] | ™ | [18 empty] | ✓
[6 empty] | ✓ |  | 7 | Order Components | [6 empty] | ™ | [17 empty] | ✓
| ✓ | [6 empty] | 8 | Apply For Graduation (Closes) | [7 empty] | ™ | [18 empty] | ✓
[6 empty] | ✓ |  | 9 | Submit Machine Shop Request | [8 empty] | ™ | [15 empty] | ✓
[6 empty] | ✓ |  | 10 | 3D Print Test Parts | [8 empty] | ™ | [16 empty] | ✓
[6 empty] | ✓ |  | 11 | Assemble General Design | [8 empty] | ™ | [14 empty] | ✓ | ✓
[7 empty] | ✓ | 12 | Begin General Testing | [9 empty] | ™ | [16 empty] | ✓
|  |  |  | ✓ |  |  |  | 13 | Update Sponsor | [10 empty] | ™ | [11 empty] | ✓ |  |  | ✓
[5 empty] | ✓ |  |  | 14 | Begin Design Refinment and Additions | [10 empty] | ™ | [15 empty] | ✓
[5 empty] | ✓ |  |  | 15 | Finalize Updated Design | [11 empty] | ™ | [14 empty] | ✓
[5 empty] | ✓ |  |  | 16 | CAD of Updated Design | [12 empty] | ™
|  |  |  | ✓ |  |  |  | 17 | Update Bill of Materials | [13 empty] | ™ | [9 empty] | ✓
[6 empty] | ✓ |  | 18 | Order Components | [13 empty] | ™ | [10 empty] | ✓
[6 empty] | ✓ |  | 19 | Assemble and Add New Components | [14 empty] | ™ | [8 empty] | ✓ | ✓
[7 empty] | ✓ | 20 | Begin Testing New Components | [15 empty] | ™ | [10 empty] | ✓
|  |  |  | ✓ |  |  |  | 21 | Update Sponsor | [16 empty] | ™ | [5 empty] | ✓ |  |  | ✓
|  |  | ✓ |  |  |  |  | 24 | Finalize Project For Presentation | [17 empty] | ™ | [6 empty] | ✓ |  | ✓
|  |  | ✓ |  |  |  |  | 25 | Engineering Design Day | [18 empty] | ™ | [7 empty] | ✓
| ✓ | [6 empty] | 26 | Last Day of Classes | [19 empty] | ™ | [6 empty] | ✓
| ✓ | [6 empty] | 27 | Final Exam Week (Opens) | [20 empty] | ™ | [5 empty] | ✓
| ✓ | [6 empty] | 28 | Final Exam Week (Closes) | [21 empty] | ™ |  |  |  |  | ✓
| ✓ | [6 empty] | 29 | Graduation | [21 empty] | ™ |  |  |  |  | ✓
[10 empty] | # People working on the project: | 4
| Academic | Homework | Presentation | Documentation | Design | Assembly | Testing |  |  |  |  | 1-3-21 | 1-10-21 | 1-17-21 | 1-24-21 | 1-31-21 | 2-7-21 | 3-14-21 | 3-16-21 | 3-28-21 | 4-4-21 | 4-11-21 | 4-18-21 | 3-23-21 | 3-24-21 | 3-26-21 | 3-27-21 | 4-6-21 | 4-16-21 | 4-19-21 | 4-23-21 | Alanna Black | Jayson Dickinson | Christina Morrow | Ryker Mullinix | All Members
Millions
[38 empty] | Budgeted | Expended
[37 empty] | #REF! | 0 | 0
[37 empty] | #REF! | 0 | 0
[37 empty] | #REF! | 0 | 0
Major Tasks
Summary & Forecast
Objectives
Target Dates
Costs