## Project timeline
PROJECT TIMELINE (SECOND SEMESTER)
Project Groups
Project Milestones
| DATE | MILESTONE | ASSIGNED TO | POSITION | Baseline
| 2024-12-30 | Complete draft of image processing code | (Mina) | 0.5 | 0
| 2025-01-06 | First day of spring semester | (All) | 6 | 0 | Project Milestones Notes
| 2025-01-06 | Begin coding for fans | (Peter, Nia) | 10 | 0 | Lab Tour and Meeting with Dr. Sweat (finalize safety details and project planning)
| 2025-01-08 | Kickoff Meeting with Sponsors | (All) | 14 | 0 | Complete draft of image processing code (workshop, maybe skeleton)
| 2025-01-10 | Arduino and necessary wire order | (Peter, Nia) | 18 | 0 | Experimental Procedures Finalized (Initial Tests and Simulant Experimental Procedures)
| 2025-01-10 | First CFD Draft | (Lawrence and Ryan) | 22 | 0
| 2025-01-10 | Simulant Selection Deadline | (Kendall) | 26 | 0
| 2025-01-10 | Schedule Ovens for Drying Simulant | (Peter, Mina, and Nia) | 3 | 0
| 2025-01-10 | Schedule Fumehood for Experiment | (Peter, Mina, and Nia) | 7 | 0
| 2025-01-10 | Wire fans to arduino | (Peter) | 11 | 0
| 2025-01-13 | Schedule Water Cutter Equipment Use | (Peter, Mina, and Nia) | 15 | 0
| 2025-01-15 | Glovebox Shipment | (Peter, Nia) | 19 | 0
| 2025-01-15 | Lab Tour and Meeting with Dr. Sweat | (All) | 23 | 0
| 2025-01-17 | Website for Team 516 Deadline | (Peter) | 27 | 0
| 2025-01-17 | Finalize CAD Model with Drawings | (Peter) | 0.5 | 0
| 2025-01-17 | Full Procurement Log Finalized | Kendall | 6 | 0
| 2025-01-17 | Finalize wiring location in glovebox | (Peter, Nia) | 10 | 0
| 2025-01-20 | Second CFD Draft | (Lawrence and Ryan) | 14 | 0
| 2025-01-24 | Run CFD Simulation | (Lawrence and Ryan) | 18 | 0
| 2025-01-24 | Determine Fan Placement | (Peter, Mina, and Nia) | 22 | 0
| 2025-02-03 | Attach latches to glovebox | (Peter, Nia) | 26 | 0
| 2025-02-12 | Safety Risk Assessment 2 | (Kendall) | 3 | 0
| 2025-02-14 | Experimental Procedures Finalized | (Kendall) | 7 | 0
| 2025-02-14 | Quality Control Check of Materials | (Mina and Kendall) | 11 | 0
| 2025-02-14 | Completion of Glovebox Parts | (Peter, Mina, and Nia) | 15 | 0
| 2025-02-21 | Materials Risk Assessment | (Kendall) | 19 | 0
| 2025-02-21 | Procedural Risk Assessment | (Kendall) | 23 | 0
| 2025-02-21 | Full Assembly of Glovebox Deadline | (Peter, Mina, and Nia) | 27 | 0
| 2025-02-28 | Sieving Simulants | (Kendall) | 0.5 | 0
| 2025-02-28 | Vacuum Test Glovebox | (Peter, Mina, and Nia) | 6 | 0
| 2025-03-03 | Test Run #1 with Simulant | (Kendall) | 10 | 0
| 2025-03-03 | Run and adjust Image Processing Code to Experiment | (Mina and Nia) | 14 | 0
| 2025-03-04 | Readjust Glovebox if needed | (Peter, Mina, and Nia) | 18 | 0
| 2025-03-04 | Compare prototype Results to CFD results (Test run) | (Lawrence and Ryan) | 22 | 0
| 2025-03-06 | Experiment Run #1 | (All) | 26 | 0
| 2025-03-07 | Mount fans inside glovebox | (Peter, Nia) | 3 | 0
| 2025-03-10 | Start of Spring Break | (All) | 7 | 0
| 2025-03-14 | End of Spring Break | (All) | 11 | 0
| 2025-03-15 | Compare prototype Results to CFD results (First run) | (Lawrence and Ryan) | 15 | 0
| 2025-03-16 | Plan Poster for Engineering Design Day | (All) | 19 | 0
| 2025-03-21 | Experiment Run #2 | (All) | 23 | 0
| 2025-03-24 | Compare prototype Results to CFD results (Second run) | (Lawrence and Ryan) | 27 | 0
| 2025-03-27 | Overall Results and Conclusion Discussion | (All) | 0.5 | 0
| 2025-03-30 | Finish Senior Design Poster | (All) | 6 | 0
| 2025-04-01 | Engnieering Design Day | (All) | 10 | 0
| 2025-04-22 | FAMU-FSU Ring Ceremony | (All) | 14 | 0
| 2025-05-02 | End of Semester | (All) | 18 | 0
| 2025-05-03 | Graduation | (All) | 22 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[5 empty] | 0 |  | SPRING TEAM DEPARTMENT | MEMBERS | RESPONSIBLTIES
[5 empty] | 0 |  | System Housing and Controls Solutions Team | MINA AND PJ AND NIA | Manufacturing box / PIV / Interior and exterior of box / Fan / Power / Cooling
[5 empty] | 0 |  | CFD Validation and Verification Team | LAWERENCE AND RYAN | CFD / Virtual Simulations (Both siumlations) / Comparing virtual and physical results
[5 empty] | 0 |  | Materials Management and Operation Logistics Team | KENDALL | Simulant / Safety / Procedure / Procurement
0
0
0
0
0
0
0
0
0