## SpringProjectPlan
PROJECT
FAMU/FSU COE Team 520 Senior Design 2024-2025
SPONSOR
Dr. Rassweiler
Spring Project Plan
WBS # | ASSIGNMENT | TASKS | START DATE | DUE DATE | PROGRESS
1 | Prototype 2: Non-Cardboard |  | 2024-11-19 | 2025-02-19
1.1 |  | Produce 3D CAD models and drawings of parts | 2024-12-01 | 2025-12-31 | Not Started
1.2 |  | Send drawings to 3D printers | 2025-01-01 | 2025-01-15 | Not Started
1.3 |  | Assemble | 2025-01-17 | 2025-01-24 | Not Started
1.4 |  | Further testing of sensors and subsystems | 2024-11-19 | 2025-02-19 | Started
1.5 |  | Creation of Electrical Diagram | 2024-12-01 | 2025-01-25 | Not Started
2 | Pre Fabrication |  | 2024-11-14 | 2025-03-01
2.1 |  | INS system development and finalization | 2024-11-14 | 2024-01-20 | Started
2.2 |  | Angle sensor development and finalization | 2024-12-01 | 2025-01-20 | Not Started
2.3 |  | Order any remaining parts intended for final product | 2024-11-19 | 2025-03-01 | Started
2.4 |  | Code integration between GPS, INS, and angle sensor | 2025-01-10 | 2025-03-01 | Not Started
2.5 |  | Path generation INS | 2025-01-10 | 2025-03-01 | Not Started
2.6 |  | Path generation GPS | 2025-01-10 | 2025-03-01 | Not Started
3 | Assembly |  | 2024-11-14 | 2025-03-27
3.1 |  | Waterproofing all systems | 2025-01-10 | 2025-03-21 | Not Started
3.2 |  | Wiring | 2024-11-14 | 2025-03-14 | Started
3.3 |  | Overlay two path generations | 2024-01-06 | 2025-03-14 | Not Started
3.4 |  | Secure all connections | 2025-01-20 | 2025-03-27 | Not Started
3.5 |  | VDR4 | 2025-02-17 | 2025-02-24 | Not Started
4 | Testing Full Assembly |  | 2024-11-14 | 2025-03-31
4.1 |  | Testing all systems above water | 2024-11-14 | 2025-03-10 | Started
4.2 |  | Testing all systems below water | 2025-03-10 | 2025-03-21 | Not Started
4.3 |  | Testing down to 10m underwater | 2025-03-10 | 2025-03-26 | Not Started
4.4 |  | Test it while jostled for travel safety | 2025-03-15 | 2025-03-30 | Not Started
4.5 |  | Troubleshoot any problems that arise | 2024-11-10 | 2024-03-31 | Started
4.6 |  | Work to finalize design | 2025-03-10 | 2024-03-31 | Not Started
4.7 |  | VDR5 | 2025-03-17 | 2025-03-24 | Not Started
5 | Finalization |  | 2025-03-25 | 2025-03-31
5.1 |  | Improve aesthics of design | 2025-03-25 | 2025-03-30 | Not Started
5.2 |  | Meet with Dr. Rassweiler and demonstrate the product in person | 2025-03-25 | 2025-03-30 | Not Started
5.3 |  | Apply changes suggested during VDR5 | 2025-03-25 | 2025-03-30 | Not Started
5.4 |  | Practice demonstrating the product for senior design day | 2025-03-26 | 2025-03-31 | Not Started
6 | Engineering Design Day |  | 2025-04-01 | 2025-04-01
6.1 |  | Setup display booth | 2025-04-01 | 2025-04-01 | Not Started
6.2 |  | Present project to the judges | 2025-04-01 | 2025-04-01 | Not Started
6.3 |  | Present project to the public | 2025-04-01 | 2025-04-01 | Not Started
6.4 |  | Cleanup display booth | 2025-04-01 | 2025-04-01 | Not Started
6.5 |  | VDR6 | 2025-04-07 | 2025-04-14 | Not Started
7 | Finals |  | 2025-04-22 | 2025-04-28
7.1 |  | Study and be on time to exam | 2025-04-28 | 2025-04-28 | Not Started
7.2 |  | A+++ | 2025-04-28 | 2025-04-28 | Not Started
8 | Graduation |  | 2024-08-26 | 2025-05-03
8.1 |  | Don't fall on stage | 2025-05-03 | 2025-05-03 | Not Started
8.2 |  | Celebrate! | 2024-08-26 | 2025-05-03 | Started