## Work Break Down Structure
PROJECT
FAMU-FSU COE Team 521 Senior Design Spring 2024
SPONSOR
Rockwell Automation
Project Schedule/Task List | [7 empty] | Important Dates
WBS # | ASSIGNMENT | Sub-Assignment | TASKS | TASK OWNER | DUE DATE | PROGRESS |  | Title | Due Date
1 | SolidWorks Model |  |  |  | 2025-01-06 | 7.5% |  | First Day of Classes | 2025-01-06
1.1 |  | Part Creation |  |  | 2025-01-06 | 12.5% |  | Design Review 4 | 2025-01-29
1.1.1 |  |  | Create all parts for the model as it currently exists | Xavier Hammond |  | 50% |  | Design Review 5 | 2025-02-18
1.1.2 |  |  | Check critical measurements of each part against actual assembly | Xavier Hammond |  | 0% |  | Spring Break | 3/10-3/15
1.1.3 |  |  | Assign accurate material for each part | Xavier Hammond |  | 0% |  | Design Review 6 | 2025-03-20
1.1.4 |  |  | Save the parts using the decided team naming format | Xavier Hammond |  | 0% |  | Engineering Design Day / VRD 6 | 2025-04-10
1.2 |  | Model Assembly |  |  | 2025-01-06 | 10% |  | Last Day of Classes | 2025-04-25
1.2.1 |  |  | Create an assembly document using the decided team naming format | Xavier Hammond |  | 50% |  | Finals Week | 4/28 - 5/2
1.2.2 |  |  | Assembly the frame of the model | Xavier Hammond |  | 0% |  | Commencement | 2025-05-02
1.2.3 |  |  | Add all parts as they currently exist | Xavier Hammond |  | 0%
1.2.4 |  |  | Ensure appropriate mates are used | Xavier Hammond |  | 0% |  | General Team Roles
1.2.5 |  |  | Check critical measurements of the model assembly against the actual assembly | Xavier Hammond |  | 0% |  | Name | Role
1.3 |  | Verification |  |  | 2025-01-06 | 0% |  | Carlos Aceituno | Mechanical Engineer
1.3.1 |  |  | Review the mates | Carlos Aceituno |  | 0% |  | Tristian Belardo | Electrical Engineer
1.3.2 |  |  | Review the included screws | Carlos Aceituno |  | 0% |  | Leah Bergman | Electrical Engineer
1.3.3 |  |  | Review critical measuremnts of the model against the actual assembly | Carlos Aceituno |  | 0% |  | Xavier Hammond | Mechanical Engineer
1.3.4 |  |  | Notify the team of model completion and share all parts | Carlos Aceituno |  | 0%
2 | SolidWorks Simulation |  |  |  | 2025-01-31 | 33.33% | * Done after SolidWorks Model
2.1 |  | Actuator Force Study |  |  | 2025-01-31 | 100%
2.1.1 |  |  | Input necessary kinematic forces | Leah Bergman |  | 100%
2.1.2 |  |  | Input necessary static forces | Leah Bergman |  | 100%
2.1.3 |  |  | Assign appropriate fixture | Leah Bergman |  | 100%
2.1.4 |  |  | Set study parameters | Leah Bergman |  | 100%
2.1.5 |  |  | Run the simulation | Leah Bergman |  | 100%
2.2 |  | Coneyor Motor Study |  |  | 2025-01-31 | 0%
2.2.1 |  |  | Input necessary motors | Xavier Hammond |  | 0%
2.2.2 |  |  | Input necessary static forces | Xavier Hammond |  | 0%
2.2.3 |  |  | Set study parameters | Xavier Hammond |  | 0%
2.2.4 |  |  | Run the simulation | Xavier Hammond |  | 0%
2.3 |  | Analysis |  |  | 2025-01-31 | 0%
2.3.1 |  |  | Find important parameters | Xavier Hammond |  | 0%
2.3.2 |  |  | Open results of important parameters | Xavier Hammond |  | 0%
2.3.3 |  |  | Exports results | Xavier Hammond |  | 0%
2.3.4 |  |  | Create a brief study update document/presentation for the team | Carlos Aceituno |  | 0%
2.3.5 |  |  | Notify the team of results via sharing the update document/presentation | Carlos Aceituno |  | 0%
3 | Frame Support |  |  |  | 2025-02-28 | 37% | *Done after SolidWorks Simulation
3.1 |  | SolidWorks Model Update |  |  | 2025-02-28 | 20%
3.1.1 |  |  | Create/import new parts to be implemented | Carlos Aceituno |  | 50%
3.1.2 |  |  | Add new parts to the current SolidWorks model | Carlos Aceituno |  | 50%
3.1.3 |  |  | Assign appropriate mates | Carlos Aceituno |  | 0%
3.1.4 |  |  | Save a copy of the model update using the decided team naming format | Carlos Aceituno |  | 0%
3.1.5 |  |  | Notify the team of model update | Carlos Aceituno |  | 0%
3.2 |  | Material Prep |  |  | 2025-02-28 | 61%
3.2.1 |  |  | Compile a list of all necessary materials | Carlos Aceituno |  | 75%
3.2.2 |  |  | Search the senior design lab for all necessary materials | Carlos Aceituno |  | 100%
3.2.3 |  |  | Confer with the team about ordering missing materials | Carlos Aceituno |  | 80%
3.2.4 |  |  | Order necessary materials | Carlos Aceituno |  | 50%
3.2.5 |  |  | Pick up materials once delivered | Carlos Aceituno |  | 0%
3.3 |  | Implementation |  |  | 2025-02-28 | 30%
3.3.1 |  |  | Measure materials | Carlos Aceituno |  | 100%
3.3.2 |  |  | Cut to necessary length | Carlos Aceituno |  | 80%
3.3.3 |  |  | Install new materials | Carlos Aceituno |  | 0%
3.3.4 |  |  | Perform safety tests | Carlos Aceituno |  | 0%
3.3.5 |  |  | Perform failure tests | Carlos Aceituno |  | 0%
3.3.6 |  |  | Notify the team of completion | Carlos Aceituno |  | 0%
4 | PLC Code |  |  |  | 2025-04-01 | 27.78%
4.1 |  | LinkedIn Course |  |  | 2025-01-06 | 75%
4.1.1 |  |  | Begin LinkedIn learning course | Tristian Belardo |  | 100%
4.1.2 |  |  | Complete LinkedIn learning course | Leah Bergman |  | 50%
4.2 |  | State Diagram |  |  | 2025-01-20 | 91.67%
4.2.1 |  |  | List necessary steps for the device to complete fully automated | Leah Bergman |  | 100%
4.2.2 |  |  | Confer with the team to determine level of automation | Leah Bergman |  | 75%
4.2.3 |  |  | Draw a state diagram based on team discussion | Leah Bergman |  | 100%
4.3 |  | Initial Code |  |  | 2025-01-31 | 0%
4.3.1 |  |  | Create a skeleton code | Tristian Belardo |  | 0%
4.3.2 |  |  | Add consise but clear comments | Tristian Belardo |  | 0%
4.3.3 |  |  | Fill in the complexities of the code | Tristian Belardo |  | 0%
4.3.4 |  |  | Add consise but clear comments | Tristian Belardo |  | 0%
4.3.5 |  |  | Review and compile the code to ensure there are no obvious errors | Tristian Belardo |  | 0%
4.4 |  | Reworked Code |  |  | 2025-02-28 | 0%
4.4.1 |  |  | Save a copy of the previous code to edit | Leah Bergman |  | 0%
4.4.2 |  |  | Note any important changes or unincluded elements | Leah Bergman |  | 0%
4.4.3 |  |  | Alter the code as necessary | Leah Bergman |  | 0%
4.4.4 |  |  | Add consise but clear comments | Leah Bergman |  | 0%
4.4.5 |  |  | Update the team via a brief document | Leah Bergman |  | 0%
4.5 |  | Test |  |  | 2025-02-28 | 0%
4.5.1 |  |  | Run the code with all wiring complete | Tristian Belardo |  | 0%
4.5.2 |  |  | Evaluate the results | Tristian Belardo |  | 0%
4.5.3 |  |  | Note any errors or questionable circumstances | Leah Bergman |  | 0%
4.5.4 |  |  | Repeat the testing until a final conclusion is reached | Leah Bergman |  | 0%
4.5.5 |  |  | Notify the team of any issues or completion | Leah Bergman |  | 0%
4.6 |  | Repeat |  |  | 2025-04-01 | 0%
4.6.1 |  |  | Rework the code as described above | Leah Bergman |  | 0%
4.6.2 |  |  | Test the code as described above | Tristian Belardo |  | 0%
4.6.3 |  |  | Notify the team as described above | Leah Bergman |  | 0%
5 | PLC Wiring |  |  |  | 2025-04-01 | 2.083%
5.1 |  | Preparation |  |  | 2025-01-31 | 6.25%
5.1.1 |  |  | List all necessary electronic components | Tristian Belardo |  | 25%
5.1.2 |  |  | Acquire all necessary components | Tristian Belardo |  | 0%
5.1.3 |  |  | Create an initial wiring diagram skeleton | Leah Bergman |  | 0%
5.1.4 |  |  | Confer with the team about the plan | Leah Bergman |  | 0%
5.2 |  | Wiring |  |  | 2025-02-28 | 0%
5.2.1 |  |  | Wire the components per the decisions of the team | Tristian Belardo |  | 0%
5.2.2 |  |  | Clean up any messy areas | Tristian Belardo |  | 0%
5.2.3 |  |  | Label all wires | Leah Bergman |  | 0%
5.2.4 |  |  | Find permament spots for all wires | Leah Bergman |  | 0%
5.2.5 |  |  | Ask another team member who was not directly involved to follow the wiring (ensures simplicity0 | Carlos Aceituno |  | 0%
5.3 |  | Wiring Diagram |  |  | 2025-04-01 | 0%
5.3.1 |  |  | Create a wiring diagram | Leah Bergman |  | 0%
5.3.2 |  |  | Ensure its accuracy to the model | Leah Bergman |  | 0%
5.3.3 |  |  | Ensure it is clear enough to follow | Leah Bergman |  | 0%
5.3.4 |  |  | Share the wiring diagram with the team | Leah Bergman |  | 0%
6 | HMI |  |  |  | 2025-04-01 | 0%
6.1 |  | Software |  |  | 2025-01-31 | 0%
6.1.1 |  |  | Download/Access necessary software | Carlos Aceituno |  | 0%
6.1.2 |  |  | Become familiar with the software | Carlos Aceituno |  | 0%
6.1.3 |  |  | Confer with Rockwell about HMI plan | Carlos Aceituno |  | 0%
6.2 |  | HMI Creation |  |  | 2025-02-28 | 0%
6.2.1 |  |  | Create the HMI via the provided software | Xavier Hammond |  | 0%
6.2.2 |  |  | Check HMI setup and progress with Rockwell | Xavier Hammond |  | 0%
6.2.3 |  |  | Create a clear and consise user manual | Xavier Hammond |  | 0%
6.3 |  | Testing/Implementation |  |  | 2025-04-01 | 0%
6.3.1 |  |  | Test the HMI with the other team members by running the device | Carlos Aceituno |  | 0%
6.3.2 |  |  | Note any points of confusion or errors | Xavier Hammond |  | 0%
6.3.3 |  |  | Provide performance evaluation to Rockwell | Xavier Hammond |  | 0%
6.3.4 |  |  | Implement Rockwell feedback | Carlos Aceituno |  | 0%
6.3.5 |  |  | Repeat the process until complete | Carlos Aceituno |  | 0%
7 | Material Storage |  |  |  | 2025-04-01 | 0%
7.1 |  | SolidWorks Model Update |  |  | 2025-03-01 | 0%
7.1.1 |  |  | Create/import new parts to be implemented | Xavier Hammond |  | 0%
7.1.2 |  |  | Add new parts to the current SolidWorks model | Xavier Hammond |  | 0%
7.1.3 |  |  | Assign appropriate mates | Xavier Hammond |  | 0%
7.1.4 |  |  | Save a copy of the model update using the decided team naming format | Xavier Hammond |  | 0%
7.1.5 |  |  | Notify the team of model update | Xavier Hammond |  | 0%
7.2 |  | Material Prep |  |  | 2025-03-31 | 0%
7.2.1 |  |  | Compile a list of all necessary materials | Carlos Aceituno |  | 0%
7.2.2 |  |  | Search the senior design lab for all necessary materials | Carlos Aceituno |  | 0%
7.2.3 |  |  | Confer with the team about ordering missing materials | Carlos Aceituno |  | 0%
7.2.4 |  |  | Order necessary materials | Carlos Aceituno |  | 0%
7.2.5 |  |  | Pick up materials once delivered | Carlos Aceituno |  | 0%
7.3 |  | Implementation |  |  | 2025-04-01 | 0%
7.3.1 |  |  | Measure materials | Carlos Aceituno |  | 0%
7.3.2 |  |  | Cut to necessary length | Carlos Aceituno |  | 0%
7.3.3 |  |  | Install new materials | Carlos Aceituno |  | 0%
7.3.4 |  |  | Perform safety tests | Xavier Hammond |  | 0%
7.3.5 |  |  | Perform failure tests | Xavier Hammond |  | 0%
7.3.6 |  |  | Notify the team of completion | Xavier Hammond |  | 0%