## Group Meetings
Group Meeting Minutes including who attended
Date | Time | Meeting Description | Team Members Present
2015-09-07 | 12:30PM - 2:00PM | Weekly meeting: Worked on Code of Conduct guidelines for the team | Anthony, Tucker, Thor, Brandon
2015-09-14 | 12:30PM - 2:00PM | Weekly meeting: Assigned jobs and tasks for each team member | Anthony, Tucker, Thor, Brandon
2015-09-21 | 12:30PM - 2:00PM | Weekly Meeting: Compiled each team member's work for the Needs Assessment Assignment | Anthony, Tucker, Thor, Brandon
2015-09-28 | 12:30PM - 2:00PM | Weekly Meeting: Discussed the budget and alternate funding | Anthony, Tucker, Thor, Brandon
2015-10-05 | 12:30PM - 2:00PM | Weekly meeting: Bought 2 Xbees and 2 Xbee controllers | Anthony, Tucker, Thor, Brandon
2015-10-08 | 1:45PM - 3:30PM | Extra Meeting: Got together to work on Project Plan and Specifications | Anthony, Tucker, Thor, Brandon
2015-10-12 | 12:30PM - 2:00PM | Weekly Meeting: Put together the Raspberry Pi | Anthony, Tucker, Thor, Brandon
2015-10-15 | 4:30PM - 7:30PM | Extra Meeting: Compiled website: -Completed each team member's About Me. -Added information to home page. -Uploaded placeholder photos. | Anthony, Tucker, Thor Absent: Brandon
2015-10-16 | 11:00AM - 6:00PM | Extra Meeting: -Meeting with Dr. Hooker and Devine at 12:00PM -Working on Midterm Presentation Testing Xbees using computers | Thor, Anthony, Tucker, Brandon
2015-10-19 | 12:30PM - 2:00PM | Weekly Meeting: Discussed midterm presentation -Multisim simulation -Power adapters | Thor, Anthony, Tucker, Brandon
2015-10-22 | 2:30PM - 4:30PM | Extra Meeting: MIDTERM PRESENATION -Prepped and rehearsed -Gave Presentation | Thor, Anthony, Tucker, Brandon
2015-10-26 | 12:30PM - 2:00PM | Weekly Meeting: Discussed Midterm Report -Divided up parts -Discussed Presentation from week before | Thor, Anthony, Tucker, Brandon
2015-11-02 | 12:30PM - 2:00PM | Weekly Meeting: -Discussed buying the Xbee breadboard device -Discussed what type of LED lights to purchase | Thor, Anthony, Tucker, Brandon
2015-11-09 | 12:30PM - 2:00PM | Weekly Meeting: - Met with Dr. Hooker to discuss what needs to be on presentation and how to improve from the previous one | Thor, Anthony, Tucker, Brandon
2015-11-16 | 12:30PM - 2:00PM | Weekly Meeting: -Discussed presentation plans -Decided on time to present | Thor, Anthony, Tucker, Brandon
2016-01-28 | 2:00PM - 10:00PM | Extra Meeting: Made major progress on both hardware and software parts of the project, including: -Backup Battery -Basic Code -Packet Comprehension | Thor, Tucker, Brandon Absent: Anthony
2016-02-01 | 12:30PM - 2:00PM | Weekly Meeting: -More Battery Testing -Discussed future plans | Thor, Tucker, Brandon Absent: Anthony
2016-02-08 | 12:30PM - 2:00PM | Weekly Meeting: -Discussed future plans -Ordered Parts | Thor, Anthony, Tucker, Brandon
2016-02-15 | 12:30PM - 2:00PM | Weekly Meeting: -Worked on XBEE communication | Thor, Anthony, Tucker, Brandon
2016-02-21 | 3:00PM - 6:00PM | Extra Meeting: -Prepare for presentation -Created demo -Slides -Shark tank Discussion (Led by Anthony | Anthony, Tucker, Thor Absent: Brandon
2016-02-29 | 12:30PM - 2:00PM | Weekly Meeting: -Discussed what would be done over break -Spoke about what was left to complete the project | Thor, Anthony, Tucker, Brandon
2016-03-21 | 12:30PM - 2:00PM | Weekly Meeting: -Spoke about slight changes / errors that need to be fixed to combine all parts of the project | Thor, Anthony, Tucker, Brandon
2016-03-24 | 2:00PM - 5:00PM | Extra Meeting: -Prepare for presentation -Created demo -Slides -Shark tank Discussion (Led by Anthony | Thor, Anthony, Tucker, Brandon
2016-03-28 | 12:30PM - 2:00PM | Weekly Meeting: -Prepared for Shark Tank | Thor, Anthony, Tucker, Brandon
2016-04-08 | 3:00PM - 8:00PM | Extra Meeting: -Finalized Everything -Finished Website (Thor) -Final Report (Anthony and Tucker) -Shark Tank Presentation (Thor and Anthony) | Anthony, Tucker, Thor Absent: Brandon

## Thor's Logbook
Thor Cutler's Lab Notebook: A list of what I have done outside of weekly group meetings and presentations
Projects: | Personal Contributions | Hours | Dates
Needs Assessment | -Wrote basic project needs -Derived Requirements from these needs | 2 | 2015-09-23
Project Plan and Specs | -Refined Requirements -Wrote test plan draft -Completed NARS document | 5 | 2015-10-08
Group Website | -Created site from scratch -Learnt basic HTML Features: -Created Home Page -Created Individual About me Pages -Created a download dropdown to collect our files -Standardized navigation bar | 15 | 10/13/15 11/20/15
Midterm Presentation/Report | -Created slides on technical parts of the design such as the Xbee specs and the User interface -Helped migrate this information to the overall report | 8 | 2015-10-19
Presentation 2 | -Created slides showing a more detailed design -Better explains how we plan to use the Xbee devices | 10 | 2015-11-18
Xbee Device Familiarization | -Learnt to have 2 Xbee devices communicate; Representative of instant messages -Learnt how to perform a capability called Pin Forwarding -Created a demonstration for Presentation 1 (Have reviewer send a message to the other) -Created a demonstration for Presentation 2 (Press a button connected to an Xbee device to light a LED connected to another one) -Started to learn API mode -Started learning basic Python integration/coding | 30 | Various
Xbee Project Use | Along with Tucker -Created code to allow for data packets to be read into an Arduino -Learnt how to read an Xbee address out of a data packet to learn which xbee sent it -Made sure that backup battery would work with the pins we chose to use (Along with Brandon) | 8 | 2016-01-28
Spring Presentation 1 | Created demo for Presentation (along with Tucker and Athoney) Created personal slides about what I've been working on since the last presentation | 5 | 2016-02-21
Xbee Project Use | Phased out needing the Arduino, allowing the Xbee receiver to communicate directly with the Raspberry Pi | 5 | 2016-03-04
Xbee Project Use | Learnt how to use the PySerial Library commands to allow the Raspberry Pi to read packets sent from the Xbee | 5 | 2016-03-05
Xbee Project Use | Created a Python Program on the Raspberry Pi that reads packets from the Xbee and saves them to a text file - Good for record keeping - Will be used by another program to display the data visually | 6 | 2016-03-06
Xbee Project Use | Along with Brandon - Created circuit that allows 2 Xbee pins to be checked as opposed to 1 - Tested using program that displays packets on the Raspberry Pi | 2 | 2016-03-21
Spring Presentation 2 | Created demo for Presentation (along with Tucker and Athoney) Created personal slides about what I've been working on since the last presentation | 5 | 2016-03-24
Shark Tank | Prepared and presented for shark tank contest (along with Anthony) | 5 | 2016-03-28
Project Finalization | Met to work on Operations Manual and code | 5 | 2016-03-31
Project Finalization | Software for user interface | 6 | 2016-04-01
Project Finalization | Software for user interface | 12 | 2016-04-02
Project Finalization | Software for user interface and updated operations manual (Along with Tucker) | 12 | 2016-04-03
Shark Tank | Market Share Research (along with Anthony) | 2 | 2016-04-10
Shark Tank | Meeting with Devine / Shark Tank Prep (along with Anthony) | 4 | 2016-04-12
Shark Tank | Created Shark Tank Slides and practiced pitch (along with Anthony) | 6 | 2016-04-13
Total |  | 158

## Tucker's Logbook
2015-08-23 | Presentation for first day of Senior Design
3 hours | Making List of requirments of a team member
2015-08-25 | Further details of project sheet
1 hour
2015-09-02 | Details to funding worked out with Dr. Devine
2 hours | Budget Created
2015-09-11 | Constraints of overall project and overal scope
2 hours
2015-09-19 | Drawing out map of duties for each Teammate and Goals for entire project
2 hours
2015-09-25 | Ordered xBee devcies and breakout boards for testing. Assessed overall
3 hours | Needs of project and found ways to impliment possible smart meter
2015-10-07 | Prepared Slides for first presentation
2 hours | Combined all other Team members slides and edited as a whole
2015-10-13 | Researched different code options availible for the Xbees
2 hours
2015-10-21 | Changed power design from Computer DC Supply to Cell Phone Adapters
2 hours | Gave information to Anthony for him to work on
2015-10-27 | Prepared Midterm report and worked on all required elements of it
8 hours
2015-11-01 | Prepared new slides on new infromation that has been added since last presentation
1 hour
2015-11-06 | Finalized slides and combined all slides from other members for presentation
3 hours
2015-11-14 | Started work on Final Report and editing on all deliverables thus far to prep for final report
3 hours
2015-11-20 | More extensive work on Final Report
3 hour
2015-11-28 | Continued work on Final report and assigning a few taks of the report to teamates
3 hours
11/31/2015 | Formating, Putting all information in and finalized editing of Final Report
5 hours
2015-12-02 | Resubmission and reediting all delverables submitted after fixing errors
8 hours | Re submission include: Midterm Report, Needs Analyisis, and Project Specificaitons
2015-01-10 | Looked into costs of 3D Printing each Streetlight Model and called around for quotes
2 hours
2015-01-18 | Got together a List of parts needed to order after asking all teammates and research
2 hours
2015-01-28 | Helped Thor create code packets to be read in the Arduino using XCTU
4 hours
2016-02-05 | Made more purchases incliuding 3D Printer Material for the buildings and Streetlight Housing
2 hours
2016-02-08 | Started learning to make 3D model STL files for 3D printing
5 hours
2016-02-10 | Started Printing 3D housing for Streetlights
9 hours
2016-02-13 | Prepared Presentation slides and grouped the teams slides together and formated all slides
3 hours
2016-02-18 | Continued 3D Printing housing and improved overall design
5 hours
2016-02-21 | Worked on Demo for presentation with Thor
2 hours
2016-02-27 | Started working on design of 3D Building
4 hours
2016-03-02 | Prepared presentation and combined all teammates slides with correct format
4 hours
2016-03-15 | Worked on 3D printing more housings and the 3D building desgin
4 hours
2016-03-25 | Started work on the Operation manual and ordered more parts
3 hours
407701 | Finished printing all Streetlight Housings and ordered additional parts
4 hours
2016-03-31 | Worked on Operation Manual as a whole
12+ hours
2016-04-02 | Finished Operation Manual and ordered more parts
3 hours
2016-04-05 | Started on Final Report and Designing 3D Stand for UI
6 hours
2016-04-07 | Continued Final Report work and Work on Circuits with Brandon
2 hours
2016-04-09 | Finished UI 3D model Continued working on Final Report
5 Hours
2016-04-10 | Started 3D Printing process for UI stand and continued working on Final Report
4 Hours
Tucker Russ Senior Design Log Book not including weekly meetings
Fall 2015 - Spring 2016 Senior Design
Dr. Jerris Hooker
Team #3 - Smart Streetlight Mesh
Project Leader
8/23/2015 to 4/10/2016

## Anthony's Logbook
Log Book: | Anthony Giordano Outside Group Meetings Fall 2015 to Spring 2016 Team 3
Date | Task | Hours
2016-09-22 | Researched streetlight specifications: Seperating distances, lighting regulations, types of lightbulbs | 4
2016-10-04 | Researched XBee specifications: Weighed options for which XBee would be best for our project compared to which XBee would be best for a real world senerio | 4
2016-10-07 | Prepared slides for presentation | 2
2015-10-20 | Smart Meter Research: Weighed options for implementing a smart meter into the Smart Streetlight project. Found the Digi XBee Smart Plug | 3
2016-11-04 | Prepared presentation slides | 2
2016-11-10 | Power Supply Design Research: Researched for ideas to give the XBee an effiecient power backup supply. Found that a 1000 mAh lithium ion battery would fit project needs | 3
2016-11-30 | Worked on final report | 3
2016-02-21 | Designed demo for presentation | 5
2016-02-25 | Began Shark Tank Research | 2
2016-03-01 | Shark Tank Workshop: Meeting with Dr. Devine to go over approach to Shark Tank Pitch (with Tucker) | 1
2016-03-01 | Prepared presentation slides | 1
2016-03-15 | Shark Tank: Researched market and other business aspect for the project to be scaled up | 2
2016-03-20 | Shark Tank: Researched market and other business aspect for the project to be scaled up | 2
2016-03-23 | Shark Tank Research | 1
2016-03-24 | Built demo for presentation (with Tucker and Thor) | 5
2016-03-26 | Prepared Shark Tank Presentation | 3
2016-03-28 | Prepared/Presented Shark Tank Presentation | 5
2016-04-02 | Worked on Operation Manual | 4
2016-04-10 | Shark Tank: Prospective market research (with Thor) | 2
2016-04-12 | Meeting Devine/Shark Tank Preperation (with Thor) | 4
2016-04-13 | Prepare Shark Tank Presentation and practice pitch (with Thor) | 6

## Brandon's Logbook
Brandon Berry Senior Design Log Book
Date | Hours | Work Done
2015-09-07 | 2 | Job delegations (weekly team meeting)
2015-09-09 | 3 | Overall Design
2015-09-14 | 3 | Overall Design (weekly team meeting)
2015-09-20 | 2 | Model Design
2015-09-21 | 3 | Design discussion (weekly team meeting)
2015-09-28 | 2 | Progress discussion(weekly team meeting)
2015-10-01 | 4 | Model Design and parts research
2015-10-05 | 4 | Progress discussion(weekly team meeting)
2015-10-06 | 3 | Model Design and parts research
2015-10-12 | 3 | Progress discussion(weekly team meeting)
2015-10-15 | 2 | Hardware Design and parts research
2015-10-19 | 1 | Progress discussion(weekly team meeting)
2015-10-26 | 2 | Progress discussion(weekly team meeting)
2015-10-28 | 4 | Hardware and model design
2015-11-02 | 2 | Progress discussion(weekly team meeting)
2015-11-03 | 4 | Circuit design
2015-11-05 | 2 | Circuit design
2015-11-09 | 2 | Progress discussion(weekly team meeting)
2015-11-10 | 2 | Battery Research
2015-11-12 | 3 | Battery Research
2015-11-16 | 4 | Progress discussion(weekly team meeting)
2015-11-23 | 1 | Progress discussion(weekly team meeting)
2015-11-30 | 2 | Progress discussion(weekly team meeting)
2015-12-02 | 4 | Overall Hardware design
2016-01-11 | 1 | Progress discussion(weekly team meeting)
2016-01-12 | 3 | Hardware parts research
2016-01-18 | 2 | Progress discussion(weekly team meeting)
2016-01-19 | 4 | Circuit building and testing
2016-01-21 | 2 | Cirucit building and testing
2016-01-25 | 2 | Progress discussion(weekly team meeting)
2016-01-26 | 3 | Hardware and software testing
2016-02-01 | 3 | Progress discussion(weekly team meeting)
2016-02-04 | 4 | Circuit building and testing
2016-02-08 | 2 | Progress discussion(weekly team meeting)
2016-02-15 | 3 | Progress discussion(weekly team meeting)
2016-02-16 | 1 | Building model
2016-02-18 | 2 | Building model
2016-02-22 | 3 | Progress discussion(weekly team meeting)
2016-02-26 | 1 | Model and hardware building
2016-02-29 | 1 | Progress discussion(weekly team meeting)
2016-03-14 | 3 | Progress discussion(weekly team meeting)
2016-03-18 | 2 | Hardware testing and editting
2016-03-21 | 3 | Progress discussion(weekly team meeting)
2016-03-24 | 3 | Model building
2016-03-28 | 2 | Progress discussion(weekly team meeting)
2016-03-30 | 3 | Building circuits
2016-03-31 | 5 | Building and testing circuits
2016-04-01 | 9 | Building and testing circuits
2016-04-04 | 3 | Progress discussion(weekly team meeting)
2016-04-04 | 4 | Circuit testing and editing